## Sheet1
Alliance Transportation Group Quality Assurance Audit Form | [9 empty] | QA Reviewer Guidance (section not to be printed with QA form)
Project Number: ______________________ | [5 empty] | Project Phase (Initiation, Major Deliverable, Closeout): ___________________
Date QA initiated: _________________________ | [5 empty] | If Major Deliverable, list: _____________________
1 - Major Finding (no evidence of effort to implement); 2 - Minor Finding (partially implemented or documented); 3 - No Finding (addressed and effectively implemented) | [7 empty] | Resolved (Yes/No) | QA Initials
|  | N/A | 1 | 2 | 3 | Comments | Actions
1 | Contract
1.1 | Is there a signed contract?
1.2 | Were the scope, schedule and budget reviewed and approved by independent leadership?
1.4 | Is there adequate budget for QA/QC?
2 | Project Planning
2.1 | Was a Project Setup Form completed?
2.2 | Is there a Project Management Plan (PMP) in place and has it been communicated with the client?
2.3 | Are QA/QC procedures defined in the PMP and are they in compliance with QA/QC provisions in the contract?
2.4 | Is a QC manager defined in the PMP (if applicable)?
2.5 | Was there a kickoff meeting in which the scope, schedule and PMP were reviewed and approved by client and the project team?
3 | Schedule
3.1 | Is there a detailed schedule that identifies milestones agreed to by the client and project team?
3.2 | Is there adequate time allowed in the schedule for QA and QC?
3.3 | Is the project on schedule?
3.4 | Are deliverables being provided to the client on time?
4 | Communications
4.1 | Is there agreement about how the Alliance PM will interact with the client?
4.2 | Are meeting agendas and minutes being prepared for all meetings?
4.3 | Is the client being consulted on all critical decisions in the project?
4.4 | Are project documents being made available to the client in a manner consistent with the contract and the PMP?
5 | Project Management
5.1 | Are project materials being stored in the appropriate project folder?
5.2 | Are invoices and progress reports being delivered to the client on time and approved by the client (A/R status)?
5.3 | Was the budget entered into Vision in a way that facilitates appropriate project budget management?
5.4 | Is Vision being used to manage the project scope and budget?
6 | Quality Control
6.1 | Was a process defined for checking the quality of data and information used in the project and is it being followed?
6.2 | Was a process defined for checking the project calculations and assessments and is it being followed?
6.3 | Are deliverables being reviewed for quality and completeness before they are delivered to the client?
6.4 | Is a standardized form being used to record the quality issues and response to the identified issues?
6.5 | Are mark-up review copies of deliverable being saved in proper PMP identified location?
7 | Quality Assurance
7.1 | Was a QA manager identified for the project?
7.2 | Are deliverables being reviewed by an independent reviewer for consistency with our contract and industry standards?
7.3 | Is the client being given the opportunity to assess the project team's performance?
7.4 | Are opportunities for innovation to give the client visibility in the profession being created?
8 | Project Closeout
8.1 | Are all QA/QC documents in the project QA/QC folder?
8.2 | Has a Project Closeout Form been completed and lessons learned been documented?
8.3 | Was Vision budget level of detail successful in project budget management?
PM and QC Manager feedback for QA process
| Date: |  |  |  |  | QA Manager:
| Date: |  |  |  |  | Project Manager:
| Date: |  |  |  |  | QC Manager (if applicable):